## work-breakdown-structure
WBS_ID | Title | Planned Effort | Real Effort | Degree og completion
1 | Project Management and Planning | 4 | 4 | 100%
1.1 | Scope Definition | 2 | 2 | 100%
1.2 | Schedule and Task Tracking | 2 | 2 | 100%
2 | Requirements and System Design | 12 | 12 | 100%
2.1 | Functional Requirements Specification | 3 | 3 | 100%
2.2 | System Architecture Diagram | 3 | 3 | 100%
2.3 | Component Selection and Procurement | 3 | 3 | 100%
2.4 | Soil Moisture Sensor Research and Calibration Plan | 3 | 3 | 100%
3 | Hardware Subsystem | 31 | 5 | 16.13%
3.1 | Prototyping Environment Setup | 2 | 1 | 50%
3.2 | Soil Moisture Sensor Integration | 4 | 0 | 0%
3.2.1 | Raw Reading Acquisition | 2 |  | 0%
3.2.2 | Calibration | 1 |  | 0%
3.2.3 | Noise Filtering | 1 |  | 0%
3.3 | Pump / Valve Subsystem | 6 | 0 | 0%
3.3.1 | Driver Circuit | 2 |  | 0%
3.3.2 | Power Path and Protection | 2 |  | 0%
3.3.3 | Flow Testing and Rate Characterization | 2 |  | 0%
3.4 | Tubing and Reservoir Mechanics | 4 | 0 | 0%
3.4.1 | Physical Layout Design | 1 |  | 0%
3.4.2 | Building and Leak Testing | 3 |  | 0%
3.5 | Power Supply | 5 | 4 | 80%
3.5.1 | Power Budget Estimation | 1 | 1 | 100%
3.5.2 | Supply Implementation | 2 | 2 | 100%
3.5.3 | Brownout / Safety Validation | 2 | 1 | 50%
3.6 | Hardware Assembly V1 | 5 |  | 0%
3.7 | Hardware Refinement V2 | 5 |  | 0%
4 | Software Subsystem | 21 | 2 | 9.524%
4.1 | Development Environment Setup | 1 | 1 | 100%
4.2 | Sensor Driver Module | 3 |  | 0%
4.3 | Moisture Data Processing | 3 |  | 0%
4.4 | Control Logic | 4 | 1 | 25%
4.5 | Actuator Control Module | 3 |  | 0%
4.6 | Data Logging | 1 |  | 0%
4.7 | User Interface / Status Output | 1 |  | 0%
4.8 | Configuration Parameters | 1 |  | 0%
4.9 | Error Handling and Fail-Safes | 2 |  | 0%
4.10 | Code Documentation | 2 |  | 0%
5 | Integration and Testing | 10 | 0 | 0%
5.1 | Hardware-Software Bring-up | 2 |  | 0%
5.2 | Calibration Procedure Execution | 1 |  | 0%
5.3 | Watering Decision Test | 2 |  | 0%
5.4 | Long-Run Stability Test | 1 |  | 0%
5.5 | Edge Case Tests | 2 |  | 0%
5.6 | Success Criteria Verification | 2 |  | 0%
6 | Documentation and Presentation | 18 | 0 | 0%
6.1 | Architecture and Design Report | 2 |  | 0%
6.2 | Calibration and Test Results Appendix | 2 |  | 0%
6.3 | User / Operation Guide | 2 |  | 0%
6.4 | Learning Reflection and Skill Development Summary | 2 |  | 0%
6.5 | Demonstration Prep | 4 |  | 0%
6.6 | Final Submission | 6 |  | 0%
| Total | 96 | 23 | 23.96%

## plan-of-progress-initial
WBS_ID | Title | Phase | Dependencies | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Planned Hours
1 | Project Management and Planning | Planning
1.1 | Scope Definition | Planning |  | Week1: 2 | 2
1.2 | Schedule and Task Tracking | Planning | 1.1 | Week2: 2 | 2
2 | Requirements and System Design | Design | 1
2.1 | Functional Requirements Specification | Design | 1.1 | Week1: 3 | 3
2.2 | System Architecture Diagram | Design | 2.1 | Week2: 3 | 3
2.3 | Component Selection and Procurement | Design | 2.1 | Week2: 3 | 3
2.4 | Soil Moisture Sensor Research and Calibration Plan | Design | 2.3 | Week3: 3 | 3
3 | Hardware Subsystem | Hardware | 2.3
3.1 | Prototyping Environment Setup | Hardware | 2.3 | Week3: 2 | 2
3.2 | Soil Moisture Sensor Integration | Hardware | 3.1
3.2.1 | Raw Reading Acquisition | Hardware | 3.2 | [13 empty] | 2 | bar: Week3 to Week4
3.2.2 | Calibration | Hardware | 3.2.1 | [13 empty] | 1 | bar: Week4
3.2.3 | Noise Filtering | Hardware | 3.2.2 | [13 empty] | 1 | bar: Week4
3.3 | Pump / Valve Subsystem | Hardware | 3.1
3.3.1 | Driver Circuit | Hardware | 3.3 | Week4: 2 | 2
3.3.2 | Power Path and Protection | Hardware | 3.3.1 | Week4: 2 | 2
3.3.3 | Flow Testing and Rate Characterization | Hardware | 3.3.2 | Week5: 2 | 2
3.4 | Tubing and Reservoir Mechanics | Hardware | 3.3.3
3.4.1 | Physical Layout Design | Hardware | 3.3.3 | [13 empty] | 1 | bar: Week5
3.4.2 | Leak and Flow Stability Tests | Hardware | 3.4.1 | Week5: 3 | 3
3.5 | Power Supply | Hardware | 3.3
3.5.1 | Power Budget Estimation | Hardware | 3.3 | [13 empty] | 1 | bar: Week4
3.5.2 | Supply Implementation | Hardware | 3.5.1 | [13 empty] | 2 | bar: Week5 to Week6
3.5.3 | Brownout / Safety Validation | Hardware | 3.5.2 | Week6: 2 | 2
3.6 | Hardware Assembly V1 | Hardware | 3.5.3 | Week6: 5 | 5
3.7 | Hardware Refinement V2 | Integration | 3.6 | Week11: 5 | 5
4 | Software Subsystem | Software
4.1 | Development Environment Setup | Software | 3.1 | [13 empty] | 1 | bar: Week7
4.2 | Sensor Driver Module | Software | 4.1 | Week7: 3 | 3
4.3 | Moisture Data Processing | Software | 4.2 | Week7: 3 | 3
4.4 | Control Logic | Software | 4.3 | Week7: 2; Week8: 2 | 4
4.5 | Actuator Control Module | Software | 4.4 | Week8: 3 | 3
4.6 | Data Logging | Software | 4.5 | [13 empty] | 1 | bar: Week8
4.7 | User Interface / Status Output | Software | 4.6 | [13 empty] | 1 | bar: Week8
4.8 | Configuration Parameters | Software | 4.4 | [13 empty] | 1 | bar: Week8
4.9 | Error Handling and Fail-Safes | Software | 4.5¦4.8 | Week8: 2 | 2
4.10 | Code Documentation (Initial) | Software | 4.9 | [13 empty] | 1 | bar: Week8
5 | Integration and Testing | Integration | 3 ¦ 4
5.1 | Hardware-Software Bring-up | Integration | 3.6¦4.5 | Week9: 2 | 2
5.2 | Calibration Procedure Execution | Integration | 5.1¦3.2.2 | [13 empty] | 1 | bar: Week9
5.3 | Watering Decision Test | Integration | 5.2 | Week9: 2 | 2
5.4 | Long-Run Stability Test | Integration | 5.3 | [13 empty] | 1 | bar: Week9
5.5 | Edge Case Tests | Integration | 5.4 | Week10: 2 | 2
5.6 | Success Criteria Verification | Integration | 5.5 | Week10: 2 | 2
6 | Documentation and Presentation | Documentation | 5.6
6.1 | Architecture and Design Report | Documentation | 5.6 | Week11: 2 | 2
6.2 | Calibration and Test Results Appendix | Documentation | 6.1 | Week11: 2 | 2
6.3 | User / Operation Guide | Documentation | 6.1 | Week10: 2 | 2
6.4 | Learning Reflection and Skill Development Summary | Documentation | 6.1 | Week12: 2 | 2
6.5 | Demonstration Prep | Documentation | 6.2¦6.3 | Week12: 4 | 4
6.6 | Final Submission | Documentation | 6.5 | Week13: 6 | 6
4.10F | Code Documentation (Final) | Documentation | 4.1 | [13 empty] | 1 | bar: Week13
|  |  | Total Hours | 5 | 8 | 6 | 8 | 7 | 8 | 9 | 11 | 6 | 6 | 9 | 6 | 7 | 96

## plan-of-progress-1
WBS_ID | Title | Phase | Dependencies | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Planned Hours
1 | Project Management and Planning | Planning
1.1 | Scope Definition | Planning |  | Week1: 2 | 2
1.2 | Schedule and Task Tracking | Planning | 1.1 | Week2: 2 | 2
2 | Requirements and System Design | Design | 1
2.1 | Functional Requirements Specification | Design | 1.1 | Week1: 3 | 3
2.2 | System Architecture Diagram | Design | 2.1 | Week2: 3 | 3
2.3 | Component Selection and Procurement | Design | 2.1 | Week2: 2; Week4: 1 | 3
2.4 | Soil Moisture Sensor Research and Calibration Plan | Design | 2.3 | Week3: 3 | 3
3 | Hardware Subsystem | Hardware | 2.3
3.1 | Prototyping Environment Setup | Hardware | 2.3 | [13 empty] | 2 | bar: Week3 to Week4
3.2 | Soil Moisture Sensor Integration | Hardware | 3.1
3.2.1 | Raw Reading Acquisition | Hardware | 3.2 | Week5: 2 | 2
3.2.2 | Calibration | Hardware | 3.2.1 | [13 empty] | 1 | bar: Week5
3.2.3 | Noise Filtering | Hardware | 3.2.2 | [13 empty] | 1 | bar: Week5
3.3 | Pump / Valve Subsystem | Hardware | 3.1
3.3.1 | Driver Circuit | Hardware | 3.3 | Week5: 2 | 2
3.3.2 | Power Path and Protection | Hardware | 3.3.1 | Week5: 2 | 2
3.3.3 | Flow Testing and Rate Characterization | Hardware | 3.3.2 | Week6: 2 | 2
3.4 | Tubing and Reservoir Mechanics | Hardware | 3.3.3
3.4.1 | Physical Layout Design | Hardware | 3.3.3 | [13 empty] | 1 | bar: Week6
3.4.2 | Leak and Flow Stability Tests | Hardware | 3.4.1 | Week6: 3 | 3
3.5 | Power Supply | Hardware | 3.3
3.5.1 | Power Budget Estimation | Hardware | 3.3 | [13 empty] | 1 | bar: Week5
3.5.2 | Supply Implementation | Hardware | 3.5.1 | Week6: 2 | 2
3.5.3 | Brownout / Safety Validation | Hardware | 3.5.2 | Week6: 2 | 2
3.6 | Hardware Assembly V1 | Hardware | 3.5.3 | Week6: 2; Week7: 3 | 5
3.7 | Hardware Refinement V2 | Integration | 3.6 | Week11: 5 | 5
4 | Software Subsystem | Software
4.1 | Development Environment Setup | Software | 3.1 | [13 empty] | 1 | bar: Week7
4.2 | Sensor Driver Module | Software | 4.1 | Week7: 3 | 3
4.3 | Moisture Data Processing | Software | 4.2 | Week7: 3 | 3
4.4 | Control Logic | Software | 4.3 | Week7: 2; Week8: 2 | 4
4.5 | Actuator Control Module | Software | 4.4 | Week8: 3 | 3
4.6 | Data Logging | Software | 4.5 | [13 empty] | 1 | bar: Week8
4.7 | User Interface / Status Output | Software | 4.6 | [13 empty] | 1 | bar: Week8
4.8 | Configuration Parameters | Software | 4.4 | [13 empty] | 1 | bar: Week8
4.9 | Error Handling and Fail-Safes | Software | 4.5¦4.8 | Week8: 2 | 2
4.10 | Code Documentation (Initial) | Software | 4.9 | Week6: 2; Week8: 1 | 3
5 | Integration and Testing | Integration | 3 ¦ 4
5.1 | Hardware-Software Bring-up | Integration | 3.6¦4.5 | Week9: 2 | 2
5.2 | Calibration Procedure Execution | Integration | 5.1¦3.2.2 | [13 empty] | 1 | bar: Week9
5.3 | Watering Decision Test | Integration | 5.2 | Week9: 2 | 2
5.4 | Long-Run Stability Test | Integration | 5.3 | [13 empty] | 1 | bar: Week9
5.5 | Edge Case Tests | Integration | 5.4 | Week10: 2 | 2
5.6 | Success Criteria Verification | Integration | 5.5 | Week10: 2 | 2
6 | Documentation and Presentation | Documentation | 5.6
6.1 | Architecture and Design Report | Documentation | 5.6 | Week11: 2 | 2
6.2 | Calibration and Test Results Appendix | Documentation | 6.1 | Week11: 2 | 2
6.3 | User / Operation Guide | Documentation | 6.1 | Week10: 2 | 2
6.4 | Learning Reflection and Skill Development Summary | Documentation | 6.1 | Week12: 2 | 2
6.5 | Demonstration Prep | Documentation | 6.2¦6.3 | Week12: 4 | 4
6.6 | Final Submission | Documentation | 6.5 | Week13: 6 | 6
4.10F | Code Documentation (Final) | Documentation | 4.1 | [13 empty] | 1 | bar: Week13
|  |  | Total Hours | 5 | 7 | 4 | 2 | 9 | 14 | 12 | 11 | 6 | 6 | 9 | 6 | 7 | 98

## plan-of-progress-2
WBS_ID | Title | Phase | Dependencies | Week37 | Week38 | Week39 | Week40 | Week41 | Week42 | Week43 | Week44 | Week45 | Week46 | Week47 | Week48 | Week49 | Planned Hours
1 | Project Management and Planning | Planning
1.1 | Scope Definition | Planning |  | Week37: 2 | 2
1.2 | Schedule and Task Tracking | Planning | 1.1 | Week38: 2 | 2
2 | Requirements and System Design | Design | 1
2.1 | Functional Requirements Specification | Design | 1.1 | Week37: 3 | 3
2.2 | System Architecture Diagram | Design | 2.1 | Week38: 3 | 3
2.3 | Component Selection and Procurement | Design | 2.1 | Week38: 2; Week40: 1 | 3
2.4 | Soil Moisture Sensor Research and Calibration Plan | Design | 2.3 | Week39: 3 | 3
3 | Hardware Subsystem | Hardware | 2.3
3.1 | Prototyping Environment Setup | Hardware | 2.3 | [13 empty] | 2 | bar: Week39 to Week40
3.2 | Soil Moisture Sensor Integration | Hardware | 3.1
3.2.1 | Raw Reading Acquisition | Hardware | 3.2 | Week43: 2 | 2
3.2.2 | Calibration | Hardware | 3.2.1 | [13 empty] | 1 | bar: Week43
3.2.3 | Noise Filtering | Hardware | 3.2.2 | [13 empty] | 1 | bar: Week43
3.3 | Pump / Valve Subsystem | Hardware | 3.1
3.3.1 | Driver Circuit | Hardware | 3.3 | Week43: 2 | 2
3.3.2 | Power Path and Protection | Hardware | 3.3.1 | Week43: 2 | 2
3.3.3 | Flow Testing and Rate Characterization | Hardware | 3.3.2 | Week43: 2 | 2
3.4 | Tubing and Reservoir Mechanics | Hardware | 3.3.3
3.4.1 | Physical Layout Design | Hardware | 3.3.3 | [13 empty] | 1 | bar: Week44
3.4.2 | Leak and Flow Stability Tests | Hardware | 3.4.1 | Week44: 3 | 3
3.5 | Power Supply | Hardware | 3.3
3.5.1 | Power Budget Estimation | Hardware | 3.3 | [13 empty] | 1 | bar: Week41
3.5.2 | Supply Implementation | Hardware | 3.5.1 | Week41: 2 | 2
3.5.3 | Brownout / Safety Validation | Hardware | 3.5.2 | [13 empty] | 2 | bar: Week41 to Week42
3.6 | Hardware Assembly V1 | Hardware | 3.5.3 | Week44: 5 | 5
3.7 | Hardware Refinement V2 | Integration | 3.6 | Week47: 5 | 5
4 | Software Subsystem | Software
4.1 | Development Environment Setup | Software | 3.1 | [13 empty] | 1 | bar: Week41
4.2 | Sensor Driver Module | Software | 4.1 | Week45: 3 | 3
4.3 | Moisture Data Processing | Software | 4.2 | Week45: 3 | 3
4.4 | Control Logic | Software | 4.3 | Week41: 1; Week42: 3 | 4
4.5 | Actuator Control Module | Software | 4.4 | Week42: 3 | 3
4.6 | Data Logging | Software | 4.5 | [13 empty] | 1 | bar: Week42
4.7 | User Interface / Status Output | Software | 4.6 | [13 empty] | 1 | bar: Week45
4.8 | Configuration Parameters | Software | 4.4 | [13 empty] | 1 | bar: Week45
4.9 | Error Handling and Fail-Safes | Software | 4.5¦4.8 | Week45: 2 | 2
4.10 | Code Documentation (Initial) | Software | 4.9 | [13 empty] | 1 | bar: Week45
5 | Integration and Testing | Integration | 3 ¦ 4
5.1 | Hardware-Software Bring-up | Integration | 3.6¦4.5 | Week46: 2 | 2
5.2 | Calibration Procedure Execution | Integration | 5.1¦3.2.2 | [13 empty] | 1 | bar: Week46
5.3 | Watering Decision Test | Integration | 5.2 | Week46: 2 | 2
5.4 | Long-Run Stability Test | Integration | 5.3 | [13 empty] | 1 | bar: Week46
5.5 | Edge Case Tests | Integration | 5.4 | Week47: 2 | 2
5.6 | Success Criteria Verification | Integration | 5.5 | Week47: 2 | 2
6 | Documentation and Presentation | Documentation | 5.6
6.1 | Architecture and Design Report | Documentation | 5.6 | Week48: 2 | 2
6.2 | Calibration and Test Results Appendix | Documentation | 6.1 | Week48: 2 | 2
6.3 | User / Operation Guide | Documentation | 6.1 | Week48: 2 | 2
6.4 | Learning Reflection and Skill Development Summary | Documentation | 6.1 | Week49: 2 | 2
6.5 | Demonstration Prep | Documentation | 6.2¦6.3 | Week49: 4 | 4
6.6 | Final Submission | Documentation | 6.5 | Week48: 6 | 6
4.10F | Code Documentation (Final) | Documentation | 4.1 | [13 empty] | 1 | bar: Week48
|  |  | Total Hours | 5 | 7 | 4 | 2 | 6 | 8 | 10 | 9 | 11 | 6 | 9 | 13 | 6 | 96